## Sheet1
Phase | Task | Description | Owner | Status
Planning & Setup | Define project goals | Write out what the dashboard is meant to accomplish and what problems it solves. | Ousmane Toure | Completed
Planning & Setup | Define scope | Decide which features are included in this version (data ingestion, cleaning, analysis) and what’s excluded. | Ousmane Toure | Completed
Planning & Setup | Identify datasets | Confirm which public datasets will be used (MITRE CVE and ECFR). | Ousmane Toure | In Progress
Planning & Setup | Set up development environment | Install Python, SQLite, and required libraries (pandas, requests, BeautifulSoup). | Ousmane Toure | Not Started
Planning & Setup | Create GitHub repository | Initialize the repository, add README, and set up folders for code, data, and documentation. | Ousmane Toure | Not Started
Planning & Setup | Draft initial README | Write a short description of the project with setup and run instructions. | Ousmane Toure | Not Started
Data Ingestion | Review dataset structure | Examine ECFR XML and CVE JSON formats to understand layout and key fields. | Ousmane Toure | Not Started
Data Ingestion | Write ECFR script | Create a Python script to fetch and save ECFR data locally. | Ousmane Toure | Not Started
Data Ingestion | Write CVE script | Build a script to download CVE data from the NVD API and store it in JSON or CSV form. | Ousmane Toure | Not Started
Data Ingestion | Add logging | Add print or log messages to track script runs and errors. | Ousmane Toure | Not Started
Data Ingestion | Test ingestion | Run both scripts and confirm the downloaded files are complete and valid. | Ousmane Toure | Not Started
Data Cleaning & Structuring | Parse ECFR data | Clean and convert ECFR XML into a simple table with sections and titles. | Ousmane Toure | Not Started
Data Cleaning & Structuring | Parse CVE data | Extract CVE ID, description, severity, and published date from the JSON files. | Ousmane Toure | Not Started
Data Cleaning & Structuring | Align schemas | Make sure ECFR and CVE data use consistent column names and formats. | Ousmane Toure | Not Started
Data Cleaning & Structuring | Handle missing data | Decide how to manage blank or inconsistent fields. | Ousmane Toure | Not Started
Data Cleaning & Structuring | Load into SQLite | Create tables in SQLite and insert the cleaned records. | Ousmane Toure | Not Started
Compliance Detection | Design database schema | Create tables for ECFR, CVE, and any matched or derived data. | Ousmane Toure | Not Started
Compliance Detection | Write matching logic | Write SQL or Python logic to detect overlapping or related entries between datasets. | Ousmane Toure | Not Started
Compliance Detection | Validate sample results | Spot-check results to make sure matches are accurate. | Ousmane Toure | Not Started
Testing | Run full pipeline | Execute scripts end-to-end and confirm outputs match expectations. | Ousmane Toure | Not Started
Testing | Debug and refine | Fix issues and clean up script flow as needed. | Ousmane Toure | Not Started
Testing | Confirm reproducibility | Re-run the project from scratch to confirm consistent results. | Ousmane Toure | Not Started
Documentation | Write project report | Draft the 3-page summary in Overleaf with objectives, methods, and results. | Ousmane Toure | Not Started
Documentation | Add dataset links | Include the public URLs for MITRE CVE and ECFR in the report appendix. | Ousmane Toure | Not Started
Documentation | Comment code | Add clear comments throughout scripts for readability. | Ousmane Toure | Not Started
Documentation | Update tracker | Keep this Excel sheet current as development continues. | Ousmane Toure | In Progress
Submission | Push final repo | Upload all project files and documentation to GitHub. | Ousmane Toure | Not Started
Submission | Submit final PDF | Upload the Overleaf report and GitHub link to Canvas. | Ousmane Toure | Not Started